## Instructions
ITC327W Project Progress and Contribution Workbook
Use this workbook throughout the semester. Update it after each project phase and submit the same workbook again so that progress can be tracked over time.
Sheet | Purpose | Evidence and Accountability Rules
Project Overview | Enter the group and project details. The dashboard summarises task progress automatically. | 1 | Every student must be assigned meaningful work in Microsoft Project.
Task Progress | Record planned and completed tasks, responsible students, dates, status, percentage completed and evidence. | 2 | Completed work must be supported by evidence such as GitHub activity, meeting records, document sections, screenshots or stakeholder communication.
Individual Contributions | Record the work personally completed by each student. Every entry must have evidence. | 3 | GitHub commits are not the only evidence. Planning, interviewing, documentation, coordination and quality review also count.
Stakeholder Engagement | Record meetings, calls and emails with the stakeholder and the main outcomes. | 4 | Do not record work as completed by a student when it was completed by someone else.
Challenges & Actions | Record project challenges, their effect and the corrective action taken. | 5 | Do not place passwords, API keys, identity numbers, private contact details or confidential records in this workbook or on GitHub.
Phase Summary | Provide a short summary of the phase, including achievements, outstanding work and participation concerns. | 6 | The confidential individual peer evaluation must be completed separately on Blackboard.
Group Reflection | Complete one shared reflection after each phase. Be honest and specific.
Recommended Update Points
|  | Unit 1 / Phase 1 | Planning, stakeholder engagement, requirements and initial SRS
|  | Phase 2 | Architecture, UML, ERD and interface design
|  | Phase 3 | Development, integration, testing and demonstration
|  | Final | Overall project summary and final reflection

## Project Overview
Project Overview and Progress Dashboard
Project Information | Group Response | Task Status | Count
Group name or number | GROUP T | Completed | 13
Project title | CLICK COMPUTER AND ACCESSORIES | In Progress | 0
Stakeholder or organisation | CLICK COMPUTER AND ACCESSORIES | Not Started | 0
Group mentor |  | Delayed | 0
Reporting phase | Phase 2 | Blocked | 0
Reporting period | 22 days | Overdue | 0
Overall status | Completed
Overall % complete | 92.86% | Contribution Summary | Count
Main achievement | Successfully completed: project documentation, system design and architecture, UML diagram, UI prototypes, stakeholder re-enagement and SRS refined documentation | Contribution entries | 10
Main challenge | A meeting re-establishment with the stakeholder for a re-evaluation of the system design and requirements | Verified entries | 10
Next planned activity | Implement and develop the final project application (including both mobile and desktop) to which must be ready for deployment | Unverified entries | 0
|  | Stakeholder engagements | 4

## Task Progress
Task Progress Tracker
Task ID | Reporting Phase | Activity | Task Description | Assigned Student | Start Date | Due Date | Status | % Complete | Evidence / Link | Verified by Group | Lecturer Comment | Progress Flag
U2-01 | Phase 2 | Activity 2.1 | Design system architecture | Mafunisa T | 2026-09-09 | 2026-09-11 | Completed | 100 | Project Documentation | Yes |  | Completed
U2-02 | Phase 2 | Activity 2.2 | Create UML diagrams | Mafunisa T,Taaibosch K | 2026-09-14 | 2026-09-17 | Completed | 100 | Project Documentation | Yes |  | Completed
U2-03 | Phase 2 | Activity 2.3 | Design database (ERD/Supabase) | Mafunisa T,Molefe sb | 2026-09-18 | 2026-09-22 | Completed | 100 | Project Documentation/Database link | Yes |  | Completed
U2-04 | Phase 2 | Activity 2.4 | Access/Security control design | Ndlovu N | 2026-09-09 | 2026-09-14 | Completed | 100 | Project Documentation | Yes |  | Completed
U2-05 | Phase 2 | Activity 2.5 | Create interface prototype (UI) | Taaibosch K | 2026-09-18 | 2026-09-23 | Completed | 100 | Project Mobile And Desktop Applications | Yes |  | Completed
U2-06 | Phase 2 | Activity 2.6 | Get stakeholder feedback on design | Tladi K | 2026-09-24 | 2026-09-25 | Completed | 100 | Stakeholder Whatsapp Screenshots, Notes, Voice Notes And Meeting Conduction | Yes |  | Completed
U2-07 | Phase 2 | Activity 2.7 | Refine design based on feedback | Mafunisa T,Taaibosch K | 2026-09-28 | 2026-09-29 | Completed | 100 | Project Documentation/Project Mobile And Desktop Applications | Yes |  | Completed
U2-08 | Phase 2 | Activity 2.8 | Refine microsoft project | Lesenyeho lj | 2026-09-09 | 2026-09-14 | Completed | 100 | Project Documentation | Yes |  | Completed
U2-09 | Phase 2 | Activity 2.9 | Requirements traceability | Hlalele D | 2026-09-09 | 2026-09-14 | Completed | 100 | Project Documentation | Yes |  | Completed
U2-10 | Phase 2 | Activity 2.10 | Refine SRS document | Hlalele D,Winkel k | 2026-09-15 | 2026-09-21 | Completed | 100 | Project Documentation | Yes |  | Completed
U2-12 | Phase 2 | Activity 2.11 | Update progress tracker | Lesenyeho lj,Winkel k | 2026-09-22 | 2026-09-24 | Completed | 100 | Project Documentation | Yes |  | Completed
U2-13 | Phase 2 | Activity 2.12 | Manage Github repository | Nosenga B | 2026-09-30 | 2026-09-30 | Completed | 100 | Github activities/pull requests | Yes |  | Completed
U2-14 | Phase 2 | Activity 2.13 | Present findings | Lesako M,Hlalele D,Lesenyeho lj,Mafunisa T,Molefe sb,Ndlovu N,Nosenga B,Taaibosch K,Tladi K,Winkel k | 2026-10-12 | 2026-10-15 | Completed | 100 | Presentation Documentation | Yes |  | Completed
Formulas:
Progress Flag = IF([Task Description]="","",IF([Status]="Completed","Completed",IF([Status]="Blocked","Blocked",IF([Status]="Delayed","Delayed",IF(AND([Due Date]<>"",[Due Date]<TODAY(),[Status]<>"Completed"),"Overdue","On Track")))))

## Individual Contributions
Individual Contribution Record
Student Name | Student Number | Reporting Phase | Activity | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Notes
LESAKO M | 221007662 | Phase 2 | Project Manager | Coordinate the complete phase 2 design and ensure that all members finish their assigned deliverables. | Coordinate all phase 2 activities; Maintain the phase 2 task list; Check that every member has a clear contribution; Coordinate integration between architecture, UML, ERD and interfaces; Organise design review meetings; Ensure designs remain within approved phase 1 scope; Coordinate final phase 2 presentation; Lead the phase 2 group reflection; Ensure all members understand their contributions for the final defence. | 2026-10-15 | 32hours | Meeting records; Task allocation; Progress tracking; Design review evidence; Github issues/tasks; Final coordination checklist; Contribution evidence. | Yes | 2026-10-15
TLADI K | 221010874 | Phase 2 | Stakeholder Analyst | Ensure that the system design reflects the stakeholder and user needs. | Review phase 1 stakeholder requirements; Identify the needs of: clients, Support operators, Technicians Administrators and Business owner; Review proposed interfaces from a user perspectives; Check whether the client journey remains simple; Prepare stakeholder feedback questions; Conduct/ coordinate stakeholder design validation; Record stakeholder comments; Identify requested changes; Ensure approved feedback is reflected in the final designs. | 2026-09-25 | 55HOURS | Stakeholder feedback questions; feedback record; meeting/communication evidence where permitted; before and after design changes; stakeholder validation/ sign-off evidence. | Yes | 2026-09-25
NOSENGA B | 223066258 | Phase 2 | Github and presentation Lead | Manage the project's design evidence and coordinate the phase 2 presentation. | Organise the phase 2 github structure; Create/ maintain folders for: Architecture, UML, ERD, Interfaces, stakeholder feedback and documentation; Ensure members commit their actual work; Track meaningful github commits; Coordinate the phase 2 presentation slides; Check that presentation content matches the portfoliio; Prepare evidence showing individual contributions; Help members prepare thier speaking sections. | 2026-09-30 | 66HOURS | GitHub commits; Issues/tasks; Branches where appropriate; Pull requests where appropriate; Presentation drafts; Final presentation; Contribution record. | Yes | 2026-09-30
MAFUNISA T | 222033930 | Phase 2 | Technical Architecture | Own the technical architecture and explain how the entire system works together. | Developed the final system architecture diagram, Supabase, architecture documentation | 2026-09-29 | 72HOURS | Architecture diagram; Architecture explanation; Data-flow explanation; Security design; Technology justification; Github commits | Yes | 2026-09-29
HLALELE D | 221003431 | Phase 2 | Requirements Analyst | Ensure that the phase 2 design can be traced directly back to phase 1 requirements. | Verify functional requirements against diagrams; Verify non-functional requirements against interface and architecture decisions; Check that no important approved requirement is missing; Identify any design element that is outside scope. | 2026-09-21 | 120HOURS | Traceability matrix; Requirement reviews; Updated design documentation; github commits. | Yes | 2026-09-21
NDLOVU N | 223038645 | Phase 2 | Risk manager | Ensure that the system design addresses security and quality requirements. | Design/ document: User roles; Authenticated flow; Authorisation; Access restrictions; Protection of user information; Supabase Row Level Security considerations; API security; Password/ security considerations; File access considerations; Error handling; Data consistency; Non-functional requirements; and Quality review. | 2026-09-14 | 70HOURS | Access-control matrix; Security design; Quality checklist; Design review; Github commits. | Yes | 2026-09-14
TAAIBOSCH K | 222001440 | Phase 2 | problem analyst | Convert the approved business processes into UML models. | Develop and document: Use Case diagram; Sequence diagrams | 2026-09-28 | 90HOURS | Use case diagram; Use case descriptions; Sequence diagrams; Version history; Design review comments. | Yes | 2026-09-28
MOLEFE B | 223019042 | Phase 2 | Feasibility Analyst | Design the database and supabase structure. | Design the phase 2 ERD and database design; Review the project's existing/ proposed entities such as: Profiles, tickets, assets, services catalog and other approved supporting structures; document supbase design. | 2026-09-22 | 320HOURS | ERD; Database dictionary; Supabase design documentation; SQL/design evidence where appropriate; Github commits. | Yes | 2026-09-22
LJ LESENYEHO | 223002326 | Phase 2 | Project planner | Update Microsoft Project and track Phase 2 progress. | Create/ update phase 2 tasks; track: start dates, finish dates, dependencies, Assigned members, progress, delays and completed tasks =. | 2026-09-24 | 54HOURS | Updated Microsoft Project; Baseline comparison; Progress reports; Task assignment evidence; Updated schedule. | Yes | 2026-09-24
WINKEL K | 221011353 | Phase 2 | Documentation and quality controller | Combine all phase 2 work into one professional design portfolio. | Maintain the phase 2 document; standardise diagram names; standardise terminology; check spelling and formatting; check that diagrams are readable; check that all sections are complete; ensure every design has an explanation; ensure stakeholder feedback is included; check that all requirements are represented; compile the final portfolio; coordinate the final group reflection document. | 2026-09-24 | 90HOURS | Portfolio versions; Quality-control checkist; Document revisions; Final portfolio; Github commits. | Yes | 2026-09-24

## Stakeholder Engagement
Stakeholder Engagement Record
Date | Reporting Phase | Type of Engagement | Purpose | Students Present | Stakeholder Present / Role | Main Findings | Action Required | Evidence / Link
2026-09-20 | Phase 2 | Email | Re-establish a meeting with the stakeholder for a re-evaulation of the system design of the application | Mafunisa T , Tladi K | YES | A date for a meeting was established and was agreed between both parties to discuss matters and issues in relations to the topic. | Contact the stakeholder via a social media platform. | Whatsapp screenshots
2026-09-24 | Phase 2 | Online Meeting | Conduct the meeting with the skateholder. | All of us | YES | Conduction of the meeting commenced on a virtual platform although, it took several minutes to enage with the stakeholder due to poor network connectivity. | The utilization of a electronic device, to which in this case a laptop and digital phone, will assist on conducting a virtual meeting. | Voice notes
2026-09-24 | Phase 2 | Online Meeting | Identify and explain key features and modifications of the system design in comparisent to previous requests to the stakeholder | Mafunisa T , Tladi K | YES | Several issues were raised and addressed to the stakeholder in comparisent to previous requests to which require modification. | Refer to the research arquired and located within the documentation. | Project documentation
2026-09-24 | Phase 2 | Online Meeting | Gather information and feedback of the skateholder in relations to the topic. | Mafunisa T , Tladi K | YES | Stakeholder understood the problem, approved on the changes and suggested on favorable alternatives. | The utilization of a recording device and tools will suffice in gathering information and feedback of the stakeholder. | stakeholder meeting notes

## Challenges & Actions
Challenges and Corrective Actions
Date Identified | Reporting Phase | Challenge | Effect on Progress | Corrective Action | Responsible Student | Target Date | Status
2026-09-24 | Phase 2 | Poor network connectivity while coducting a meeting with the stakeholder. | Poor communication while interacting; words are vague thus a loss of understanding; poor network connectivity results to a time dilation | Move to a less dense traffic congested network to obtain better connectivity. | TLADI K | 2026-09-24 | Resolved
2026-09-18 | Phase 2 | Few members lacked sufficient skills and thus incapable for rendering the system prototype. | Work was delayed; stress and tension manifests therefore leading to negative health conditions. | Seek for assistance within the group | MOLEFE B | 2026-09-24 | Resolved
2026-09-12 | Phase 2 | Group was oblivious to their role | Members become stagnated and therefore under perform or do not participant | Report to the project manager for a role clarification. | HLALELE D, TLADI K, NDLOVU N | 2026-09-24 | Resolved
2026-09-09 | Phase 2 | The utilization of artificial intelligence was misintepreted and therefore misused. | A member's entire work was replicated from an artificial intelligence open source application. | The utilization of artificial intelligence must only be used as a research material or as a references based on one's individual work. | TAAIBOSH K | 2026-09-12 | Resolved
2026-09-22 | Phase 2 | Some team members were absent / arrived late when the meeting was over | Work and tasks were delayed; members seldom participate, engage nor socially interact. | Team collaboration via a social media platform. | LESAKO M | 2026-09-24 | Resolved
2026-09-19 | Phase 2 | Conflicts between members | Social presure resulting to disorganized or delayed work; | Collaborate with eachother rather than argue. | MAFUNISA T, NOSENGA B, MOLEFE B | 2026-09-24 | Resolved

## Phase Summary
Phase Progress Summary
Summary Information | Group Response | Phase Completion Checklist
Reporting phase | Phase 2 | Initial or updated SRS completed | Yes
Reporting period | 2 weeks | Progress report updated | Yes
Overall phase status | Completed | Individual contributions recorded | Yes
What was completed during this phase? | Activity 2.1 - Design system architecture; Activity 2.2 - Create UML diagrams; Activity 2.3 - Design database (ERD/Supabase); Activity 2.4 - Access/Security control design; Activity 2.5 - Create interface prototype (UI); Activity 2.6 - Get stakeholder feedback on design; Activity 2.7 - Refine design based on feedback; Activity 2.8 - Refine microsoft project; Activity 2.9 - Requirements traceability; Activity 2.10 - Refine SRS document; Activity 2.11 - Update progress tracker; Activity 2.12 - Manage Github repository; Activity 2.13 - Present findings | Stakeholder engagement recorded | Yes
What remains incomplete? | none. | Challenges and actions updated | Yes
Why is it incomplete? | N/A | Group reflection completed | Yes
Which contributions were particularly important? | The project manager's contribution was to ensure all members were available for crucial and urgent meetings when deemed necessary. When members lacked participation or remained absent, it is the project manager's reponsibility to contact, follow-up and enquire an update on each and every members' work; The responsibility of a Github manager contributed by ensuring all files uploaded onto the Github repository were managed, accurate and up-to-date. Members were assisted and informed to upload and identify thier own work onto the repository due to system monitorization; The system design and the prototype was most crucial as it required the collaboration of three members: The database and supbase design analyst, the technical analyst and intergration designer and the UML and process analyst to design, create and integrate the database system and mobile and web applications; Lastly, the responsibility of a stakeholder analyst is one of the most vital contribution to pahse 2. Gathering stakeholder feedback and re-evaluation could shift the entire prespective of the system design. | Microsoft Project updated | Yes
Were there participation concerns? | Conflicts emerged amongst members due to work delay and lagging of time; A member was absent for two consecutive meetings to which raised concerns within the group; Finally, participation amongst the group was a minor issue as few do not assist in contributing. | GitHub evidence available | Yes
What will the group improve in the next phase? | Collaboration between members will be essential for the next phase; Skill enhancement is required for the next phase in completion to the final system development; and the diminishing use of artificial intelligence will help avoid in replicating one's own work. | Confidential peer check completed | Yes
Main priority for the next phase | Understand system development and integration; Set up and implent the shared supabase backend; Develop the flutter mobile application; Develop the ASP.NET web application; and integrate the mobile and web application.

## Group Reflection
Group Reflection
Reflection Information | Group Response | Reflection Guidance
Reporting phase | Phase 2 | Length | Approximately 300–400 words in total.
Project title | Click_Computer_Accessories | Focus | Discuss the group’s actual experience, not the activity instructions.
Most important learning from this phase | What the group have learnt from this phase are; the ability to collaborate as a group; review the authenticity of our work with less reliance on external sources; and exert a systematic approach to completing tasks. | Honesty | Identifying a genuine challenge will not disadvantage the group when an improvement action is provided.
What went well and why? | The project documentation offers feasible information due to evident claims. These documents includes; project schedule, software requirements specification (SRS), project tracker, requirements traceability documentation and stakeholder feedback on design notes. | Evidence | Ensure that claims about participation agree with the contribution record, Microsoft Project and GitHub.
What was difficult and why? | There was poor network connectivity while conducting a meeting with the stakeholder due to a large sum of traffic interception; Few members lacked sufficient skills and thus incapable for rendering the system prototype; Some members in the group were oblivious to their role within the initial period of this phase due to a sudden change of objectives prior to phase 1; The utilization of artificial intelligence was misintepreted and therefore misused; and some team members were absent / arrived late when the meeting was over thus resulting to conflicts between eachother. | Research use | Student work may only be used for research after the required ethical approval and consent processes.
How were tasks divided among members? | Tasks were divided according to the members' roles; 1.The project manager coordinates and delegate tasks to members as well as ensuring their completion; 2. The Github, presentation and design evidence lead manages the project's design evidence and coordinate phase 2 presentation; 3. UML and process analyst was responsible for converting the approved business process into UML models; 4. the requirements traceability and UML analyst ensures the design can be traced directly to phase 1 requirements; 5. the technical architect and integration designer was responsible in designing the technical aspect of the system as well as integrate it with other systems; 6. the database and supabase design analyst designs the database and supabase structure; 7. the security, access control and quality analyst ensures that the system design addresses security and quality requirements; 8. the project planner and phase 2 progress manager updates the project schedule and tracks phase 2 progress; 9. the documentation, quality assurance and portfolio lead combines phase 2 work into one professional design portfolio; and 10. the stakeholder and user experience analyst ensures that the system design reflects the stakeholder and user needs.
Did all members contribute fairly? Explain. | Yes. Eventually, all members contributed to their designated roles. Despite initial performances, the contribution record shows a balanced distribution of effort, with each member taking ownership of specific sections of the project.
How did the group handle disagreements or delays? | When disagreements arose within the group, it will usually resort to work being delayed and disorganized as well as the manifestation of stress and tension between members thus creating a less ethical work environment. The optimal solution was to address the issue and resolve it through collaboration. On the other hand, when team members were absent or delayed, tasks and work was delayed as well and participation gradually diminishes. This issue was resolved by communicating via a social media platform - Whatsapp.
What did the group learn from the stakeholder? | Our re-enagement with the stakeholder sufficed in gathering favorable alternatives of the design of the system than those to which we deemed inconcievable to design and implement. In addition, unrealistic/abstract proposals presented by the stakeholder as a source for the software requirements specification can always be rectified.
Improvement action 1 for the next phase | Collaboration between members will be essential for the next phase.
Improvement action 2 for the next phase | Skill enhancement is required for the next phase in completion to the final system development.
Priority for the next phase | Understand system development and integration; Set up and implent the shared supabase backend; Develop the flutter mobile application; Develop the ASP.NET web application; and integrate the mobile and web application.