## Instructions
ITC327W Phase 2 Project Progress Tracker
Use this workbook during Phase 2: System Architecture and Design. Update it throughout the phase and submit the same workbook with Assessment 2.
Sheet | Purpose | What must be kept current
Project Overview | Group details and automatic progress summary | Group information, GitHub link and current Phase 2 progress
Design Progress | Track each design artefact and supporting work | Architecture, UML, ERD, mobile/web interfaces, SRS and project-management tasks
Individual Contributions | Record work personally completed by each student | Activity, responsibility, work completed and evidence
Design Source Links | Record editable source links/files for submitted designs | Architecture, UML, ERD, mobile and web design sources
Challenges & Actions | Record design/project challenges and corrective action | Problem, effect, action, owner, target date and status
Phase Summary | Summarise what was achieved and what remains | Phase status, completed work, gaps and next priorities
Group Reflection | One shared group reflection for Phase 2 | Participation, collaboration, challenges, learning and improvements
Important
Do not create a separate tracker for each activity. This Phase 2 workbook is updated as the group progresses. Evidence may include GitHub commits, screenshots, document sections, editable design links/files and other appropriate project evidence. Do not include passwords, API keys or confidential stakeholder information.

## Project Overview
Phase 2 Project Overview
Group | GROUP T | Phase 2 Progress Summary
Project Title | CLICK COMPUTER AND ACCESSORIES | Total tracked items | 12
Stakeholder / Organisation | CLICK COMPUTER AND ACCESSORIES | Completed | 11
Group Leader | Lesako Mpho | In Progress | 1
Number of Group Members | 10 | Blocked | 0
GitHub Repository Link | https://github.com/tmafunisa24-sudo | Average completion | 95.83%
Reporting Period | 4 weeks (14 Sep - 13 Oct 2026)
Overall Phase Status | In Progress | Phase 2 Reminder
Phase 2 focuses on system architecture and design. Track the design artefacts, the editable source links/files, individual contributions, challenges, Microsoft Project updates and GitHub evidence. No separate stakeholder-evidence section is required in this tracker.

## Design Progress
Phase 2 Design Progress
Task ID | Design / Project Item | Description / Expected Output | Responsible Student(s) | Planned Date | Actual Completion Date | Status | % Complete | Evidence / Link | Notes / Action Required
P2-01 | System Architecture | Overall architecture showing Flutter, ASP.NET and shared Supabase backend | Mafunisa T | 2026-09-17 | 2026-09-22 | Completed | 100% | System architecture diagram | Flutter, ASP.NET and Supabase shown as one integrated system.
P2-02 | Use Case Diagram | Actors, use cases, system boundary and appropriate UML relationships | Tladi K, Molefe B, Lesako M | 2026-10-02 | 2026-10-05 | Completed | 100% | Use Case Diagram
P2-03 | Sequence Diagram 1 | Important Flutter process | Taaibosch K, Winkel K, Ndlovu N | 2026-10-02 | 2026-10-07 | Completed | 100% | Sequence Diagrams (Flutter/Supabase and ASP.NET/Supabase) | Group drafted the final version together so everyone agreed on it.
P2-04 | Sequence Diagram 2 | Important ASP.NET process | Taaibosch K, Winkel K, Ndlovu N | 2026-10-02 | 2026-10-07 | Completed | 100% | Sequence Diagrams (Flutter/Supabase and ASP.NET/Supabase) | Created together with Sequence Diagram 1.
P2-05 | ERD | Entities, attributes, PKs, FKs, relationships and cardinality | Molefe B | 2026-09-21 | 2026-09-21 | Completed | 100% | ERD | ERD for the Supabase backend.
P2-06 | Flutter Interface Designs | Main mobile screens and navigation | Nosenga B | 2026-10-05 | 2026-10-07 | Completed | 100% | Wireframe Flutter
P2-07 | ASP.NET Interface Designs | Main web pages and navigation | Nosenga B, Mafunisa T | 2026-10-05 | 2026-10-07 | Completed | 100% | Wireframes 2 ASP.NET
P2-08 | Design Alignment | Requirements linked across UML, ERD and interfaces | Taaibosch K, Winkel K, Ndlovu N, Molefe B, Lesako M, Tladi K | 2026-10-09 | 2026-10-09 | Completed | 100% | Updated design files; MS Project task 2.6; stakeholder acceptance register | Designs refined after stakeholder feedback (task 2.6).
P2-09 | Updated SRS | Phase 2 architecture and design section inserted in existing SRS | Hlalele D, Lesako M | 2026-10-11 | 2026-10-12 | Completed | 100% | SRS Version 3.0 PDF | Phase 1 + Phase 2 combined in a single PDF.
P2-10 | Microsoft Project | Schedule updated to reflect design progress and upcoming development | Lesenyeho LJ | 2026-10-09 | 2026-10-09 | Completed | 100% | Updated MS Project file and screenshot | Schedule updated for Phase 2 (task 2.7).
P2-11 | GitHub | Current design documentation and repository organisation | Nosenga B, Lesenyeho LJ, Lesako M | 2026-10-09 | 2026-10-09 | Completed | 100% | GitHub repository; progress tracker | Phase 2 documentation and tracker updated on GitHub (task 2.7).
P2-12 | Phase 2 Presentation | Presentation and defence preparation | Hlalele D (lead presenter) | 2026-10-16 |  | In Progress | 50% |  | Presentation and defence scheduled for 16 Oct 2026.

## Individual Contributions
Phase 2 Individual Contributions
Student Name | Student Number | Activity / Artefact | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Quality / Review Notes | Contribution Status
LESAKO M | 221007662 | Project Manager | Coordinate Phase 2; take part in stakeholder acceptance; create the second set of wireframes. | Took part in the stakeholder acceptance meeting, created the second set of wireframes, and led the action on late/absent members at meetings (fine and group-chat communication). | 2026-10-07 | 12 | Use case, stakeholder acceptance record; group chat | Yes | 2026-10-08 | the work was coordinated well | Completed
TLADI K | 221010874 | Stakeholder Analyst | Create the Use Case Diagram; take part in stakeholder acceptance. | Created the Use Case Diagram and took part in the stakeholder acceptance meeting. | 2026-10-05 | 12 | Use Case Diagram | Yes | 2026-10-08 | the use case was completed and the group accepted . | Completed
NOSENGA B | 223066258 | GitHub and presentation Lead | Maintain the GitHub repository; take part in stakeholder acceptance; create wireframes. | Maintained the GitHub repository with the Phase 2 documentation, took part in the stakeholder acceptance meeting and created the wireframes. | 2026-10-09 | 7 | GitHub repository; stakeholder acceptance record; wireframes | Yes | 2026-10-10 | wireframes, and github repo were completed and met stakeholder requirements. | Completed
MAFUNISA T | 222033930 | Technical Architecture | Design the system architecture; take part in stakeholder acceptance; refine designs. | Designed the system architecture, took part in the stakeholder acceptance meeting and refined the designs after feedback. | 2026-09-22 | 14 | System architecture diagram; stakeholder acceptance record | Yes | 2026-09-25 | The architecture explained the project in short. | Completed
HLALELE D | 221003431 | Requirements Analyst | Update the SRS (Version 3.0) and lead the Phase 2 presentation. | Updated the SRS to Version 3.0 with the new System Architecture and Design section (task 2.8); lead presenter for Phase 2. | 2026-10-12 | 9 | SRS Version 3.0 | Yes | 2026-10-12 | SRS 3.0 was build on stakeholder accepted designs | Completed
NDLOVU N | 223038645 | Risk manager | Create the sequence diagrams. | Created the Sequence Diagrams together with Winkel K and Taaibosch K; the group finalised the version everyone agreed on; refined the designs after feedback. | 2026-10-07 | 12 | Sequence diagrams | Yes | 2026-10-09 | The Sequence Diagrams were redrafted together until everyone agreed, and they refined the designs after feedback. | Completed
TAAIBOSCH K | 222001440 | Problem analyst | Create the Sequence Diagrams; refine designs. | Created the Sequence Diagrams together with Winkel K; the group finalised the version everyone agreed on; refined the designs after feedback (2.6). | 2026-10-07 | 14 | Sequence Diagrams | Yes | 2026-10-09 | The Sequence Diagrams were redrafted together until everyone agreed, and they refined the designs after feedback. | Completed
MOLEFE B | 223019042 | Feasibility Analyst | Design the ERD. | Designed the Entity Relationship Diagram (ERD) for the Supabase database. | 2026-09-21 | 11 | ERD | Yes | 2026-09-25 | The ERD was complete and the group aggreed upon Iit. | Completed
LJ LESENYEHO | 223002326 | Project planner | Create and update the Microsoft Project plan. | Created and updated the Microsoft Project plan for Phase 2. | 2026-10-09 | 6 | Microsoft Project file / screenshot | Yes | 2026-10-10 | the schedule was updated to reflect Phase 2 design progress | Completed
WINKEL K | 221011353 | Documentation and quality controller | Create the Sequence Diagrams. | Created the Sequence Diagrams together with Taaibosch K and Ndlovu N. | 2026-10-07 | 13 | Sequence Diagrams | Yes | 2026-10-09 | The Sequence Diagrams were redrafted together until everyone agreed, and they refined the designs after feedback. | Completed
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started

## Design Source Links
Phase 2 Original Design Source Links / Files
Design Artefact | Tool Used | Editable Link / File Name | Accessible to Lecturer? | Last Updated | Responsible Student | Included in SRS? | Notes
System Architecture | Draw .io | https://drive.google.com/file/d/11Ja90b6tMq4ahkI-THez3RUYbPcuNtIx/view?usp=sharing | Yes | 2026-10-02 | Mafunisa T | Yes | Editable link/file name still to be added.
Use Case Diagram | LucidChart | https://lucid.app/lucidchart/895a8e0d-97e9-4649-a7c0-7f30062eb435/edit?viewport_loc=-7250%2C10394%2C4256%2C3450%2C0_0&invitationId=inv_13a5c578-a00c-4381-bcc7-15b1d5d87536 | Yes | 2026-10-09 | Tladi K, Molefe B, Lesako M | Yes | https://lucid.app/lucidchart/895a8e0d-97e9-4649-a7c0-7f30062eb435/edit?viewport_loc=-10144%2C3206%2C6538%2C3456%2C0_0&invitationId=inv_13a5c578-a00c-4381-bcc7-15b1d5d87536
Sequence Diagram 1 | LucidChart | https://lucid.app/lucidchart/ec36d4bc-a084-4884-bbed-d6398301ee8f/edit?viewport_loc=-9560%2C-2792%2C5464%2C2212%2C0_0&invitationId=inv_8c3b9894-ed5e-43c1-9f78-075a273945f1 | Yes | 2026-10-09 | Taaibosch K, Winkel K, Ndlovu N | Yes | https://lucid.app/lucidchart/ec36d4bc-a084-4884-bbed-d6398301ee8f/edit?viewport_loc=-4456%2C-2900%2C5464%2C2212%2C0_0&invitationId=inv_8c3b9894-ed5e-43c1-9f78-075a273945f1
Sequence Diagram 2 | LucidChart | https://lucid.app/lucidchart/ec36d4bc-a084-4884-bbed-d6398301ee8f/edit?viewport_loc=-9560%2C-2792%2C5464%2C2212%2C0_0&invitationId=inv_8c3b9894-ed5e-43c1-9f78-075a273945f1 | Yes | 2026-10-09 | Taaibosch K, Winkel K, Ndlovu N | Yes | https://lucid.app/lucidchart/ec36d4bc-a084-4884-bbed-d6398301ee8f/edit?viewport_loc=-4456%2C-2900%2C5464%2C2212%2C0_0&invitationId=inv_8c3b9894-ed5e-43c1-9f78-075a273945f1
ERD | LucidChart | https://lucid.app/lucidchart/57c2cd7d-a52f-4d36-aba6-b10b1a96a3e2/edit?viewport_loc=-4225%2C-1950%2C8513%2C6900%2C0_0&invitationId=inv_4eaa2ff6-389d-47f4-8048-3caf7578fdf2 | Yes | 2026-09-25 | Molefe B | Yes | https://lucid.app/lucidchart/57c2cd7d-a52f-4d36-aba6-b10b1a96a3e2/edit?viewport_loc=-1456%2C392%2C5464%2C2212%2C0_0&invitationId=inv_4eaa2ff6-389d-47f4-8048-3caf7578fdf2
Flutter Interface Designs | Figma | https://www.figma.com/design/IsuW8QCf5vvCxYrkFC2KOq/ServiceHub-IT---Design-System---Prototypes?node-id=111-667&t=AklSjmxOGRMnR2Wq-1Prototypes?node-id=1-2&t=WDTaxEEDC0oUVDfr-1 | Yes | 2026-10-09 | Nosenga B | Yes | https://www.figma.com/design/IsuW8QCf5vvCxYrkFC2KOq/ServiceHub-IT---Design-System---Prototypes?node-id=1-2&t=WDTaxEEDC0oUVDfr-1
ASP.NET Interface Designs | Figma | https://www.figma.com/design/IsuW8QCf5vvCxYrkFC2KOq/ServiceHub-IT---Design-System---Prototypes?node-id=111-667&t=AklSjmxOGRMnR2Wq-1 | Yes | 2026-10-09 | Nosenga B, Mafunisa T | Yes | https://www.figma.com/design/IsuW8QCf5vvCxYrkFC2KOq/ServiceHub-IT---Design-System---Prototypes?node-id=1-2&t=WDTaxEEDC0oUVDfr-1
Navigation Flow |  | https://www.figma.com/design/IsuW8QCf5vvCxYrkFC2KOq/ServiceHub-IT---Design-System---Prototypes?node-id=111-667&t=AklSjmxOGRMnR2Wq-1 | Yes | 2026-10-09 | Nosenga B | Yes | https://www.figma.com/design/IsuW8QCf5vvCxYrkFC2KOq/ServiceHub-IT---Design-System---Prototypes?node-id=1-2&t=WDTaxEEDC0oUVDfr-1

## Challenges & Actions
Phase 2 Challenges and Corrective Actions
Date Identified | Challenge | Effect on Progress / Design | Corrective Action | Responsible Student | Target Date | Status | Resolved Date | Notes
2026-09-25 | During group meetings most members arrived late or did not attend. | Meetings could not run with the full group, which slowed decisions and the coordination of tasks. | A fine was introduced for members who did not comply, and the behaviour was addressed on the group chat. This was led by Mpho Lesako. | LESAKO M | 2026-10-05 | Completed | 2026-10-05
2026-10-05 | Understanding the diagrams: each member took a turn at drawing diagrams, and the Sequence Diagrams were the most confusing. | Members did not all understand the diagrams in the same way. | The group sat together and drafted the Sequence Diagrams that everyone agreed on. | ALL MEMBERS | 2026-10-09 | Completed | 2026-10-09
2026-10-12 | Five members were not present during our meeting to finalise everything before submission. | Decision making and acceptance were delayed. | We communicated later on WhatsApp. | ALL MEMBERS | 2026-10-12 | Completed | 2026-10-12
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started

## Phase Summary
Phase 2 Progress Summary
Reporting Period | 4 weeks (14 Sep - 13 Oct 2026) | Phase 2 Completion Checklist | Complete?
Overall Phase Status | Completed | Architecture complete | Yes
What was completed during Phase 2? | We designed the system architecture showing the Flutter mobile app, ASP.NET web app and shared Supabase backend as one integrated system; created the Use Case Diagram and Sequence Diagrams; designed the ERD for the Supabase database; created the Flutter and ASP.NET wireframes; obtained stakeholder acceptance of the designs; and refined the designs after feedback. The Microsoft Project plan, GitHub repository and progress tracker were updated and SRS Version 3.0 (Phase 1 + Phase 2) was finalised. | Use Case Diagram complete | Yes
What remains incomplete? | The Phase 2 presentation and defence (16 Oct 2026) .Development of the Flutter, ASP.NET and Supabase components follows in Phase 3. | Two Sequence Diagrams complete | Yes
Why is it incomplete? | The presentation depends on the completed and refined designs and the final SRS, so it is scheduled on the 16th of October 2026 in our Microsoft Project. | ERD complete | Yes
Which contributions were particularly important? | Mafunisa T designed the system architecture. Tladi K created the Use Case Diagram. Taaibosch K, Winkel K and Ndlovu N created the Sequence Diagrams. Molefe B designed the ERD. Nosenga B created the wireframes and maintained GitHub. Lesako M coordinated Phase 2 and, with Tladi K, Mafunisa T and Nosenga B, took part in the stakeholder acceptance meeting. Lesenyeho LJ updated the Microsoft Project plan and Hlalele D finalised SRS Version 3.0. | Flutter interfaces complete | Yes
Were there participation concerns? | Yes. During group meetings most members arrived late or did not attend. The group introduced a fine for members who did not comply and addressed the behaviour on the group chat, led by Mpho Lesako. | ASP.NET interfaces complete | Yes
What will the group improve in Phase 3? | For Phase 3 we will record each member's contributions and evidence at the time the work is done, keep Microsoft Project and this tracker updated every week, and use a shared checklist before each submission. | Editable source links/files recorded | Yes
Main priority for Phase 3 | Phase 3: develop the Flutter mobile app, the ASP.NET web app and the Supabase integration according to the approved designs, then test, correct and prepare the demonstration. | SRS updated | Yes
|  | Microsoft Project updated | Yes
|  | GitHub current | Yes
|  | Individual contributions recorded | Yes
|  | Challenges/actions updated | Yes
|  | Group reflection completed | Yes

## Group Reflection
Phase 2 Group Reflection
1. What did the group complete successfully during Phase 2?
The group turned the Phase 1 requirements into the system architecture, Use Case Diagram, two Sequence Diagrams, ERD and Flutter and ASP.NET wireframes. The designs were presented to the stakeholder, who accepted them, and they were refined after feedback. The Microsoft Project plan, GitHub repository and progress tracker were updated and SRS Version 3.0 was finalised.
2. Which architecture or design activities were the most challenging?
Two things were difficult. Most members arrived late or did not attend group meetings, which made it hard to coordinate. Understanding the diagrams was also difficult, because each member took a turn at drawing diagrams and the Sequence Diagrams were the most confusing.
3. How did the group ensure that Flutter, ASP.NET and Supabase were designed as one integrated system?
The architecture, Use Case Diagram, Sequence Diagrams, ERD and wireframes all had to trace back to the same approved requirements. The architecture showed Flutter and ASP.NET both using the shared Supabase backend, the ERD was designed for that backend, and the database had to support every screen and page. Refining the designs together after stakeholder feedback kept them consistent.
4. How was work divided among group members, and was participation balanced?
Every member was given a Phase 2 task: Mafunisa T the system architecture, Tladi K the Use Case Diagram, Taaibosch K, Winkel K and Ndlovu N the Sequence Diagrams, Molefe B the ERD, Nosenga B the wireframes and GitHub, Lesenyeho LJ the Microsoft Project plan and Hlalele D the SRS update. Attendance at meetings was not consistent, so participation was not fully balanced, which is why the group introduced a fine and addressed it on the group chat.
5. What did the group learn from developing the UML, ERD and interface designs?
The architecture, UML, ERD and interface designs must all describe the same system, and designing before coding helped us find gaps early. Drawing the Sequence Diagrams together showed that each member can read a diagram differently, so the group needs a shared understanding before finalising any design.
6. What will the group do differently during development in Phase 3?
In Phase 3 we will record contributions and evidence at the time the work is done, update Microsoft Project and the tracker weekly, and use a shared checklist before each submission to check that every file, link, diagram and record is complete, consistent and accessible.