## Instructions
ITC327W Project Progress and Contribution Workbook
Use this workbook throughout the semester. Update it after each project phase and submit the same workbook again so that progress can be tracked over time.
Sheet | Purpose | Evidence and Accountability Rules
Project Overview | Enter the group and project details. The dashboard summarises task progress automatically. | 1 | Every student must be assigned meaningful work in Microsoft Project.
Task Progress | Record planned and completed tasks, responsible students, dates, status, percentage completed and evidence. | 2 | Completed work must be supported by evidence such as GitHub activity, meeting records, document sections, screenshots or stakeholder communication.
Individual Contributions | Record the work personally completed by each student. Every entry must have evidence. | 3 | GitHub commits are not the only evidence. Planning, interviewing, documentation, coordination and quality review also count.
Stakeholder Engagement | Record meetings, calls and emails with the stakeholder and the main outcomes. | 4 | Do not record work as completed by a student when it was completed by someone else.
Challenges & Actions | Record project challenges, their effect and the corrective action taken. | 5 | Do not place passwords, API keys, identity numbers, private contact details or confidential records in this workbook or on GitHub.
Phase Summary | Provide a short summary of the phase, including achievements, outstanding work and participation concerns. | 6 | The confidential individual peer evaluation must be completed separately on Blackboard.
Group Reflection | Complete one shared reflection after each phase. Be honest and specific.
Recommended Update Points
|  | Unit 1 / Phase 1 | Planning, stakeholder engagement, requirements and initial SRS
|  | Phase 2 | Architecture, UML, ERD and interface design
|  | Phase 3 | Development, integration, testing and demonstration
|  | Final | Overall project summary and final reflection

## Project Overview
Project Overview and Progress Dashboard
Project Information | Group Response | Task Status | Count
Group name or number | GROUP T | Completed | 17
Project title | CLICK COMPUTER AND ACCESSORIES | In Progress | 0
Stakeholder or organisation | CLICK COMPUTER AND ACCESSORIES | Not Started | 1
Group mentor |  | Delayed | 0
Reporting phase | Unit 1 and 2/ Phase 1 | Blocked | 0
Reporting period | 2 weeks | Overdue | 0
Overall status | Completed
Overall % complete | 94.44% | Contribution Summary | Count
Main achievement | Successfully completed stakeholder engagement, SRS Version 2.0, feasibility analysis, risk register, and all project documentation | Contribution entries | 10
Main challenge | The main challenge was finding a stakeholder and he was unavailable during the first site visit, requiring a second visit | Verified entries | 10
Next planned activity | Submit final project package and prepare for Unit 3/Phase 2 (System Design & Development) | Unverified entries | 0
|  | Stakeholder engagements | 3

## Task Progress
Task Progress Tracker
Task ID | Reporting Phase | Activity | Task Description | Assigned Student | Start Date | Due Date | Status | % Complete | Evidence / Link | Verified by Group | Lecturer Comment | Progress Flag
U1-01 | Unit 1 / Phase 1 | Activity 1.1 | Identify and confirm the external stakeholder | TLADI K ,MAFUNISA T | 2026-08-24 | 2026-08-25 | Completed | 100 | Stakeholder site visit -24 AUG 2026 | Yes |  | Completed
U1-02 | Unit 1 / Phase 1 | Activity 1.1 | Document the current process and problem | TAAIBOSCH K | 2026-08-25 | 2026-08-26 | Completed | 100 | Stakeholder descussion and problem analysis notes- 25 AUG 2026 | Yes |  | Completed
U1-03 | Unit 1 / Phase 1 | Activity 1.1 | Define the project aim, objectives and scope | MOLEFE SB | 2026-08-25 | 2026-08-27 | Completed | 100 | stakeholder interview question document | Yes |  | Completed
U1-04 | Unit 1 / Phase 1 | Activity 1.2 | Prepare stakeholder interview questions | TLADI K ,MAFUNISA T | 2026-08-24 | 2026-08-24 | Completed | 100 | stakeholder meeting notes -25AUG 2026 | Yes |  | Completed
U1-05 | Unit 1 / Phase 1 | Activity 1.2 | Conduct and document the stakeholder interview | TLADI K ,MAFUNISA T | 2026-08-25 | 2026-08-25 | Completed | 100 | Visit the stakeholder to conduct an interview | Yes |  | Completed
U1-06 | Unit 1 / Phase 1 | Activity 1.2 | Collect all the risks and feasibility study | NDLOVU N , MOLEFE SB | 2026-08-25 | 2026-08-27 | Completed | 100 | feasibility study template and risk register | Yes |  | Completed
U1-07 | Unit 1 / Phase 1 | Activity 1.3 | Compile the initial SRS | HLALELE D | 2026-08-25 | 2026-08-27 | Completed | 100 | initial SRS document | Yes |  | Completed
U1-08 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Microsoft Project schedule | LJ LESENYEHO | 2026-08-26 | 2026-08-27 | Completed | 100 | microsoft project schedule | Yes |  | Completed
U1-09 | Unit 1 / Phase 1 | Activity 1.3 | Create and configure the GitHub repository | NOSENGA B | 2026-08-25 | 2026-08-25 | Completed | 100 | Github repositorr/README | Yes |  | Completed
U1-10 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Supabase project | MAFUNISA T | 2026-08-25 | 2026-08-26 | Completed | 100 | supabase project setup | Yes |  | Completed
[7 empty] | Not Started |  |  | Yes
U1-11 | Unit 1 / Phase 1 | Activity 2.1 | Conduct technical, economic, operational, schedule, legal and ethical feasibility analysis | MOLEFE SB | 2026-08-27 | 2026-08-29 | Completed | 100 | Feasibility study analysis | Yes |  | Completed
U1-12 | Unit 1 / Phase 1 | Activity 2.2 | Develop project risk register with mitigation and contingency plans | NDLOVU N | 2026-08-27 | 2026-08-29 | Completed | 100 | risk register | Yes |  | Completed
U1-13 | Unit 1 / Phase 1 | Activity 2.3 | Refine SRS requirements, create change log and refined scope | HLALELE D | 2026-08-28 | 2026-08-30 | Completed | 100 | srs document | Yes |  | Completed
U1-14 | Unit 1 / Phase 1 | Activity 2.3 | Update stakeholder register and compile engagement evidence | TLADI K | 2026-08-28 | 2026-08-30 | Completed | 100 | stakeholder register and analysis | Yes |  | Completed
U1-15 | Unit 1 / Phase 1 | Activity 2.3 | Define system architecture and technology stack | MAFUNISA T | 2026-08-28 | 2026-08-29 | Completed | 100 | Technical analysis document | Yes |  | Completed
U1-16 | Unit 1 / Phase 1 | Activity 2.3 | Finalize SRS Version 2.0 document (Unit 1 + 2 combined) | WINKEL K, LESAKO M | 2026-08-29 | 2026-09-02 | Completed | 100 | Updated SRS document | Yes |  | Completed
U1-17 | Unit 1 / Phase 1 | Activity 2.3 | Complete progress report, contribution record and group reflection | LESAKO M | 2026-08-30 | 2026-09-02 | Completed | 100 | Project Documentation | Yes |  | Completed
Formulas:
Progress Flag = IF([Task Description]="","",IF([Status]="Completed","Completed",IF([Status]="Blocked","Blocked",IF([Status]="Delayed","Delayed",IF(AND([Due Date]<>"",[Due Date]<TODAY(),[Status]<>"Completed"),"Overdue","On Track")))))

## Individual Contributions
Individual Contribution Record
Student Name | Student Number | Reporting Phase | Activity | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Notes
LESAKO M | 221007662 | Unit 1 / Phase 1 | Project Manager | Coordinate the whole project, deadlines, meetings and final submission. | I coordinated the entire project, ensured objectives were met, managed the change log, and finalized the SRS Version 2.0 for submissionhelped create the srs,ric=sk template and feasibility questions and template. | 2026-09-02 | 10hours | SRS, Risk Register and Feasibility Questions, progress tracker | Yes | 2026-08-02
TLADI K | 221010874 | Unit 1 / Phase 1 | Stakeholder Analyst | Develop stakeholder register, engagement evidence, requirements confirmation and sign-off. | Develop stakeholder register, engagement evidence, requirements confirmation and sign-off. | 2026-08-30 | 7HOURS | Stakeholder Register / Engagement Evidence | Yes | 2026-08-30
NOSENGA B | 223066258 | Unit 1 / Phase 1 | Github and presentation Lead | Maintain GitHub evidence, README, presentation and presentation coordination. | Maintained the GitHub repository, updated the README and assisted with presentation preparation and coordination. | 2026-08-30 | 8HOURS | GitHub Repository / README / Presentation | Yes | 2026-08-30
MAFUNISA T | 222033930 | Unit 1 / Phase 1 | Technical Architecture | Develop technology stack, architecture, integration and technical solution. | Developed the proposed technology stack and documented the system architecture, integration approach and technical solution. | 2026-08-29 | 7HOURS | Technical Architecture Document | Yes | 2026-08-30
HLALELE D | 221003431 | Unit 1 / Phase 1 | Requirements Analyst | Identify and document functional/non-functional requirements and SRS requirements. | Identified and documented functional and non-functional requirements and contributed to the Software Requirements Specification (SRS). | 2026-08-30 | 7HOURS | SRS / Requirements Document | Yes | 2026-08-31
NDLOVU N | 223038645 | Unit 1 / Phase 1 | Risk manager | Develop risk register, probability/impact assessment, mitigation and contingency plans | Developed the project risk register, identified potential risks, assessed probability and impact, and proposed mitigation and contingency plans. | 2026-08-29 | 7HOURS | Risk Register | Yes | 2026-08-29
TAAIBOSCH K | 222001440 | Unit 1 / Phase 1 | problem analyst | Analyse the problem situation, current process, business needs, objectives and benefits. | Analysed the problem situation, current processes, business needs, project objectives and expected benefits of the proposed system. | 2026-08-27 | 6HOURS | Problem Statement / Business Analysis | Yes | 2026-08-28
MOLEFE B | 223019042 | Unit 1 / Phase 1 | Feasibility Analyst | Assess technical, economic, operational, schedule, legal and social/cultural feasibility. | Conducted the technical, economic, operational, schedule, legal and social/cultural feasibility assessment | 2026-08-29 | 7HOURS | Feasibility Study | Yes | 2026-08-30
LJ LESENYEHO | 223002326 | Unit 1 / Phase 1 | Project planner | Develop WBS, Microsoft Project schedule, dependencies, resources and milestones. | Developed the WBS and initial Microsoft Project schedule, including activities, dependencies, resources and milestones. | 2026-08-27 | 7HOURS | Microsoft Project Schedule | Yes | 2026-08-30
WINKEL K | 221011353 | Unit 1 / Phase 1 | Documentation and quality controller | Maintain master documentation, formatting, consistency, and final rubric check. | Maintained the master project document and reviewed the assessment requirements | 2026-09-02 | 9HOURS | Project Documentation | Yes | 2026-09-02

## Stakeholder Engagement
Stakeholder Engagement Record
Date | Reporting Phase | Type of Engagement | Purpose | Students Present | Stakeholder Present / Role | Main Findings | Action Required | Evidence / Link
2026-08-24 | Unit 1 / Phase 1 | Site Visit | To find a stakeholder so work with | Mafunisa T , Tladi K | NO | The stakeholder was not presentand his assistant made an appointment for us | Arrange a confirmed meeting with the stakeholders | site visit notes
2026-08-25 | Unit 1 / Phase 1 | Site Visit | To meet with the stakeholder in person | Mafunisa T , Tladi K | YES | The stakeholder agreed to work with us and gave us a clear understanding of the problem he faces. | Document the stakeholders problem, requirements and agreed next steps | stakeholder meeting notes
2026-08-26 | Unit 1 / Phase 1 | Online Meeting | Tcommunicate with the stakeholder to get final understanding of what is needed of us | All of us | YES | The stakeholder gave us a cleatre understanding of what is expected and what do we need to include in the scope he already gave us. | Update the document and add changes mentioned by the stakeholder to the requirements. | Whatsapp screenshots

## Challenges & Actions
Challenges and Corrective Actions
Date Identified | Reporting Phase | Challenge | Effect on Progress | Corrective Action | Responsible Student | Target Date | Status
2026-08-24 | Unit 1 / Phase 1 | Stakehholder was not available during the first site visit | The team could not complete the stakeholder discussion on the first visit | Assistant arranged an appointment and the team returned for a confirmed satkeholder meeting | Mafunisa T | 2026-08-25 | Resolved
2026-08-24 | Unit 1 / Phase 1 | Some team members were absent / arrived late when the meeting was over | The group was not able to assign roles to all team members | We communicated later on whatsapp and set another date to meet | Lesako M | 2026-08-26 | Resolved
Resolved
2026-08-25 | Unit 1 / Phase 1 | The feasibility analysis required more research than anticipated, especially for legal and ethical feasibility. | The feasibility section was delayed by one day. | The feasibility analyst (Molefe B) prioritised research and consulted online legal resources and the stakeholder for clarification | MOLEFE B | 2026-08-29 | Resolved
2026-08-27 | Unit 1 / Phase 1 | GitHub repository had merge conflicts due to multiple team members uploading files simultaneously | The repository became temporarily disorganised, and some files were overwritten. | .The GitHub lead resolved the merge conflicts, established a clear file-naming convention, and instructed the team to push changes one at a time. | NOSENGA B | 2026-08-30 | Resolved
2026-08-27 | Unit 1 / Phase 1 | The risk register required more detailed mitigation and contingency plans than initially planned. | The risk section took longer to complete, affecting the final SRS compilation. | The risk manager worked extra hours to complete the risk register with detailed mitigation and contingency plans. | NDLOVU N | 2026-08-29 | Resolved
2026-08-30 | Unit 1 / Phase 1 | Final document formatting and consistency checks took longer than expected. | The final submission was at risk of being delayed. | The documentation lead and project manager worked together on the final day to complete all formatting, proofreading, and final checks. | LESAKO M , WINKEL K | 2026-08-31 | Resolved

## Phase Summary
Phase Progress Summary
Summary Information | Group Response | Phase Completion Checklist
Reporting phase | Unit 1 and 2 / Phase 1 | Initial or updated SRS completed | Yes
Reporting period | 2 weeks | Progress report updated | Yes
Overall phase status | Completed | Individual contributions recorded | Yes
What was completed during this phase? | The group identified and confirmed Click Computer and Accessories as the stakeholder, completed the stakeholder interview, clarified the main problem, compiled the initial SRS (Version 1.0), set up GitHub, created the Supabase project, conducted a full feasibility analysis (technical, economic, operational, schedule, legal and ethical), developed a comprehensive risk register with mitigation and contingency plans, refined the SRS to Version 2.0, updated the stakeholder register, and finalised all project documentation for submission. | Stakeholder engagement recorded | Yes
What remains incomplete? | All tasks have been completed. The final submission package (SRS Version 2.0, progress tracker, contribution records, challenges log, phase summary, and group reflection) is now ready for submission. | Challenges and actions updated | Yes
Why is it incomplete? | Some activities required more time than anticipated. The first stakeholder visit had to be followed by a second visit because the stakeholder was initially unavailable. Additional time was also needed to complete the feasibility analysis, risk register, and final document formatting. | Group reflection completed | Yes
Which contributions were particularly important? | The project manager coordinated the entire project and ensured all deadlines were met. The stakeholder analyst handled stakeholder engagement and requirements confirmation. The problem analyst focused on defining the problem and objectives. The requirements analyst worked on the functional and non-functional requirements and SRS. The technical architect defined the system architecture and technology stack. The project planner created the WBS and Microsoft Project schedule. The GitHub lead managed the repository and presentation. The feasibility analyst conducted the comprehensive feasibility study. The risk manager developed the risk register. The documentation and quality controller maintained formatting consistency and performed the final quality assurance check. | Microsoft Project updated | Yes
Were there participation concerns? | Some team members were absent or arrived late during the initial meeting, which delayed role assignments. However, these concerns were resolved through WhatsApp communication and a follow-up meeting. All contribution records have now been updated with the actual work and evidence collected by each member. | GitHub evidence available | Yes
What will the group improve in the next phase? | For Phase 2 (Design & Development), we will: update the Microsoft Project schedule immediately as design and coding tasks are assigned; record each member's contributions and evidence in real-time; and use a shared checklist before each submission to ensure consistency and completeness. | Confidential peer check completed | Yes
Main priority for the next phase | For Phase 2, we need to prioritize the actual system design and development. This includes designing the Flutter mobile frontend UI/UX, building the ASP.NET Core Web API backend, setting up and integrating Supabase for the database, updating the Microsoft Project schedule for Phase 2 tasks, ensuring all evidence is verified and stored on GitHub, and preparing the group for the transition from planning to building the solution.

## Group Reflection
Group Reflection
Reflection Information | Group Response | Reflection Guidance
Reporting phase | Unit 1 / Phase 1 | Length | Approximately 300–400 words in total.
Project title | Click_Computer_Accessories | Focus | Discuss the group’s actual experience, not the activity instructions.
Most important learning from this phase | The most important learning from Phase 1 (Planning & Analysis) was that a project depends on having a real stakeholder who can provide genuine insight into the business problem. Without a clear understanding of the "as-is" situation and the stakeholder's needs, it is impossible to define realistic requirements or design a feasible solution. This phase taught us that thorough planning and stakeholder engagement are not just administrative steps, but are the foundation for all subsequent project work.. | Honesty | Identifying a genuine challenge will not disadvantage the group when an improvement action is provided.
What went well and why? | The group successfully identified and confirmed Click Computer and Accessories as a willing stakeholder. The second site visit was highly productive because the stakeholder was available and explained their current processes and pain points in detail. This allowed the team to divide tasks effectively according to each member's assigned role, and the project manager coordinated the work to ensure deadlines were met. The stakeholder's input was also critical in shaping the technical architecture, risk register, feasibility study, and project planning. | Evidence | Ensure that claims about participation agree with the contribution record, Microsoft Project and GitHub.
What was difficult and why? | The first visit was difficult because the stakeholder was not available.This meant the team could not complete the discussion on the first visit.The group had to arrange the another appointment and return.Some project documentation still needed time to be completed. | Research use | Student work may only be used for research after the required ethical approval and consent processes.
How were tasks divided among members? | Tasks were divided according to the members;roles.The project manager coordinated all the work ,Requirements analyst focused on the requirements,problem analyst on the problem,stakeholder analyst on the stakeholder,while other members handles the documentation, technical architecture,risk, reasibility ,planning, github and supabase.
Did all members contribute fairly? Explain. | Yes, all members contributed to their designated roles. The contribution record shows a balanced distribution of effort, with each member taking ownership of specific sections of the SRS and project documents. The stakeholder was also able to provide feedback to all members, which ensured that everyone understood the project from the same perspective.
How did the group handle disagreements or delays? | vOur main challenge was the stakeholder's unavailability on the first scheduled visit. Instead of proceeding with incomplete information, we handled this delay professionally by immediately rescheduling a new appointment. We also addressed team member lateness by reallocating tasks temporarily and using WhatsApp to communicate and set a new meeting time for role assignments. This taught us to be proactive and flexible when facing setbacks.
What did the group learn from the stakeholder? | We learned that the stakeholder's explanation of the current manual process was invaluable. It helped us define realistic functional and non-functional requirements for the SRS, conduct a meaningful feasibility analysis, and set achievable project objectives. The stakeholder meeting gave the group a much clearer direction for the project and confirmed that our proposed solution would genuinely address their needs.
Improvement action 1 for the next phase | For Phase 2 (Design & Development), we will ensure that the Microsoft Project schedule is updated immediately as design and coding tasks are assigned, and that each member's actual contributions and evidence are recorded in real-time, rather than retrospectively. This will help us track progress on the Flutter frontend, ASP.NET Core backend, and Supabase integration more effectively.
Improvement action 2 for the next phase | For Phase 2, we will use a shared checklist before each submission to ensure that every task, piece of evidence, and contribution is thoroughly reviewed and consistent. This will prevent last-minute formatting and quality assurance issues, especially as we move from planning to building the actual system.
Priority for the next phase | For Phase 2, we need to prioritize the actual system design and development. This includes designing the Flutter mobile frontend UI/UX, building the ASP.NET Core Web API backend, setting up and integrating Supabase for the database, updating the Microsoft Project schedule for Phase 2 tasks, ensuring all evidence is verified and stored on GitHub, and preparing the group for the transition from planning to building the solution.