## Instructions
ITC327W Phase 3 Project Progress Tracker
Use this workbook during Phase 3: System Development, Implementation and Final Demonstration. Update it throughout the phase and submit the same workbook with Assessment 3.
Sheet | Purpose | What must be kept current
Project Overview | Group details and automatic development summary | Project details, GitHub link and current Phase 3 progress
Development Progress | Track implementation work | Supabase, Flutter, ASP.NET, integration, SRS, GitHub, Microsoft Project and demonstration preparation
Individual Contributions | Record work personally completed by each student | Activity, responsibility, completed work and evidence
Integration Progress | Track important shared processes across the system | Flutter action, ASP.NET action, shared Supabase information and current working status
Implementation Evidence | Record evidence of the working prototype | Screenshots, recordings, GitHub commits/links and relevant SRS sections
Challenges & Actions | Record development/integration challenges and corrective action | Problem, effect, action, owner, target date and status
Phase Summary | Summarise Phase 3 progress | Completed work, limitations, participation and final readiness
Group Reflection | One shared final group reflection | Development experience, collaboration, challenges and lessons learned
Important
Phase 3 does not require a formal test plan, test cases or defect log. Record normal development checks, working functions, integration progress, challenges and corrections as part of implementation. Do not include passwords, API keys or confidential stakeholder/user information.

## Project Overview
Phase 3 Project Overview
Group | GROUP T | Phase 3 Development Summary
Project Title | CLICK COMPUTER AND ACCESSORIES | Total tracked items | 13
Stakeholder / Organisation | CLICK COMPUTER AND ACCESSORIES | Completed | 13
Group Leader | Lesako M | In Progress | 0
Number of Group Members | 10 | Blocked | 0
GitHub Repository Link | https://github.com/tmafunisa24-sudo/ITC327W-Project | Average completion | 100%
Reporting Period | 18 days
Overall Phase Status | Completed | Phase 3 Reminder
Phase 3 focuses on implementing and demonstrating the integrated prototype. Track the shared Supabase backend, Flutter mobile application, ASP.NET web application, important shared processes, GitHub evidence, Microsoft Project and the final demonstration.

## Development Progress
Phase 3 Development Progress
Task ID | Development Area | Task / Function | Responsible Student(s) | Planned Date | Actual Completion Date | Status | % Complete | Evidence / GitHub Link | Notes / Action Required
P3-01 | Supabase Backend | Required tables, fields, keys and relationships implemented | Molefe sb, Lesako M | 2026-10-16 | Completed | Completed | 100% | Project Documentation/Database link
P3-02 | Supabase Backend | Authentication and access configured where required | Molefe sb | 2026-10-19 | Completed | Completed | 100% | Project Documentation/Database link
P3-03 | Flutter | Approved mobile screens and navigation implemented | Nosenga B | 2026-10-16 | Completed | Completed | 100% | Project Mobile Applications
P3-04 | Flutter | Main mobile functions connected to Supabase | Nosenga B | 2026-10-21 | Completed | Completed | 100% | Project Mobile Applications
P3-05 | ASP.NET | Approved web pages and navigation implemented | Mafunisa T | 2026-10-16 | Completed | Completed | 100% | Project Web Applications
P3-06 | ASP.NET | Main web functions connected to Supabase | Mafunisa T | 2026-10-21 | Completed | Completed | 100% | Project Web Applications
P3-07 | Integration | Shared Process 1 working across the integrated system | Taaibosch K, Ndlovu N | 2026-10-23 | Completed | Completed | 100% | Database link, Project Mobile Applications, Project Web Applications
P3-08 | Integration | Shared Process 2 working across the integrated system | Taaibosch K, Winkel k | 2026-10-23 | Completed | Completed | 100% | Database link, Project Mobile Applications, Project Web Applications
P3-09 | Integration | Data fields and status values consistent across applications | Taaibosch K, Ndlovu N | 2026-10-27 | Completed | Completed | 100% | Database link, Project Mobile Applications, Project Web Applications
P3-10 | SRS | Implementation status, approved changes and known limitations updated | Hlalele D | 2026-10-29 | Completed | Completed | 100% | Project Documentation
P3-11 | Microsoft Project | Schedule updated to reflect actual development progress | Lesenyeho lj | 2026-10-16 | Completed | Completed | 100% | Project Documentation
P3-12 | GitHub | Current source code, README and relevant documentation organised | Nosenga B | 2026-11-02 | Completed | Completed | 100% | Github activities/pull requests
P3-13 | Final Demonstration | Prototype and demonstration flow prepared for panel | Lesako M,Hlalele D,Lesenyeho lj,Mafunisa T,Molefe sb,Ndlovu N,Nosenga, Taaibosch K, Winkel k, Tladi K | 2026-11-10 | Completed | Completed | 100% | Presentation Documentation

## Individual Contributions
Phase 3 Individual Contributions
Student Name | Student Number | Development Area | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / GitHub Link | Verified by Group | Verification Date | Quality / Review Notes | Contribution Status
LESAKO M | 221007662 | GitHub | Manage the project's design evidence and coordinate the phase 3 presentation. | Organise the phase 3 github structure; Upload web and mobile applications (ASP.NET and Flutter) and documentation; Ensure members commit their actual work; Track meaningful github commits; Prepare evidence showing individual contributions; | 2026-11-02 | 24 | https://github.com/tmafunisa24-sudo/ITC327W-Project | Yes | 2026-11-02 |  | Completed
TLADI K | 221010874 | Final Demonstration | Coordinate the phase 3 presentation. | Help members prepare thier speaking sections. | 2026-11-03 | 24 | Presentation Documentation | Yes | 2026-11-02 |  | Completed
NOSENGA B | 223066258 | Flutter | Design mobile screens, functions, navigation and connect to Supabase. | Use Visual code to create functions, screens and connect the application to the supabase. | 2026-10-22 | 48 | Mobile application | Yes | 2026-11-02 |  | Completed
MAFUNISA T | 222033930 | ASP.NET | Implement web pages and navigations. | Use Visual studio to create functions and web pages with the C# and CSHtml programming language. | 2026-10-22 | 48 | Web application | Yes | 2026-11-02 |  | Completed
HLALELE D | 221003431 | SRS | Document implementation status, approved changes and limitations. | Collect documents; evaluate the status of the web and mobile application; review changes rendered on the applications and; render screenshot as evidence. | 2026-10-30 | 48 | Project Documentation | Yes | 2026-11-02 |  | Completed
NDLOVU N | 223038645 | Integration | Shared process 1 | Integrate the web application with the supabase application. | 2026-10-26 | 48 | Web application and database link | Yes | 2026-11-02 |  | Completed
TAAIBOSCH K | 222001440 | Integration | Shared process 2 | Integrate the mobile application with the supabase application. | 2026-10-26 | 48 | Mobile application and database link | Yes | 2026-11-02 |  | Completed
MOLEFE B | 223019042 | Supabase Backend | Design the database and supabase structure. | Implement the database and ensure all related tables are connected through key variables. | 2026-10-20 | 24 | Database link | Yes | 2026-11-02 |  | Completed
LJ LESENYEHO | 223002326 | Microsoft Project | Update Microsoft Project and track Phase 3 progress. | Create/ update phase 3 tasks; track: start dates, finish dates, dependencies, Assigned members, progress, delays and completed tasks. | 2026-10-19 | 48 | Project documentation | Yes | 2026-11-02 |  | Completed
WINKEL K | 221011353 | ASP.NET | Connect Supabase to ASP.NET web application. | Ensure information coming from the database is reflected and displayed onto the web application. | 2026-10-22 | 48 | Web application | Yes | 2026-11-02 |  | Completed
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started

## Integration Progress
Phase 3 Shared Process and Integration Progress
Shared Process | Related Requirement / Use Case | Flutter Action | ASP.NET Action | Shared Supabase Information | Current Status | Responsible Student(s) | Evidence / Link | Notes / Limitation
Login and role-based landing on mobile and web. | Authentication & Access control | views/auth, auth api/service/viewmodel, core/network/*, profile_view | AuthController, AuthApiController, Views/Auth/*, StatusAuthorizationFilter, RoleDashboardRoute, auth DTOs | username, password | Completed | LESAKO M | Github Branch Name: "feature/mpho-lesako-auth"
Client creates a ticket on mobile | Tickets - mobile and API | views/tickets/*, ticket api/service/viewmodel, create_ticket_viewmodel, ticket models/DTOs, payment DTO | ImageStorageService, Services/Ai/TicketPredictionModel, TicketAttachment/TicketPrediction models | Client details, ticket details | Completed | MAFUNISA T | Github Branch Name: "feature/godfrey-nosenga-interface"
Notification triggered and shown. | Notifications, technician & service catalog | views/notification, notification_bell, technician_home_view, service catalog files | Notifications controller/API/service/model/views, TechnicianController + views, technician DTOs, ServiceCatalogApiController | Notifications | Completed | MOLEFE B | Github Branch Name: "feature/blessing-molefe-notifications-knowledge"
Status | UI shell, docs & project records | core/design/*, app.dart, routes/app_router, shell_scaffold, main.dart | _Layout.cshtml, site.css/js, Home/KnowledgeBase/Employee views + controllers | Employee information | Completed | HLALELE D & NOSENGA B | Github Branch Name: "feature/dineo-hlalele-helpdesk" and " feature/godfrey-nosenga-interface"
Role dashboards and report export | Dashboard and reports | home_view, client_home_view, dashboard_widgets, report_view, dashboard/report api/service/viewmodel | DashboardController, ReportsController, their APIs/services, dashboard & report views and DTOs | Report, client details, files and documentation. | Completed | TAAIBOSCH K | Github Branch Name: "feature/kamogelo-taaibosch-dashboards"
Maintenance records create/update | Maintenance | views/maintenance/*, maintenance api/service/viewmodel/models | MaintenanceController, MaintenanceApiController, maintenance models/DTOs, Views/Maintenance/* | product, model and asset details | Completed | TLADI K | Github Branch Name: "feature/keletso-tladi-departments-maintenance"
Asset list/details on web and mobile | Assets | views/assets/*, asset api/service/viewmodel/models | Both AssetsControllers, AssetsApiController, AssetService, PdfProcessingService, asset models, Views/Assets + Views/Admin/Assets | assest details | Completed | WINKEL K | Github Branch Name: "feature/katlego-winkel-assets"
Departments and users management | Departments, users & admin | views/departments, views/users, admin_home_view, department/user api/service/viewmodel | DepartmentsController (both), DerpartmentsApiController, UsersApiController, AdminController, Views/Admin/*, Views/Departments/* | Department, user and admin names | Completed | LJ LESENYEHO | Github Branch Name: "feature/liteboho-lesenyeho-admin"
Supabase tables, relationship; roles of Flutter, ASP.NET and Supabase | Supabase backend & DevOps | core/config/env.dart | NEW: supabase/schema.sql, RLS policies, seed.sql, bucket setup. Existing: Program.cs, SupabaseService, ISupabaseService, BaseRepository, RequestLoggingMiddleware, SupabaseSettings, AppConstants | Database tables | Completed | MOLEFE B | Github Branch Name: "feature/"
Ticket appears in web admin/technician queue | Tickets - web and API | (none - mobile side is Member 2) | TicketsController, HelpDeskController, TicketsApiController, TicketService, ticket models/DTOs, Views/Tickets/*, Views/HelpDesk/*, tickets.css, Payment | Client details, ticket details | Completed | NDLOVU N | Github Branch Name: "feature/ntando-ndlovu-tickets"
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started

## Implementation Evidence
Phase 3 Implementation Evidence
Evidence ID | Application / Area | Function / Feature | Evidence Type | Evidence / Link / File | Related SRS Requirement | Responsible Student | Notes
P3-01 | Supabase Backend | External Database Storage | Supabase Evidence | https://qcfniphdrgoonaviatwn.supabase.co | System requires a database to store in information. | MOLEFE B
P3-03 | Flutter | Mobile application | GitHub Commit/PR | https://github.com/tmafunisa24-sudo/ITC327W-Project/mobile | System requires a mobile interface. | NOSENGA B
P3-05 | ASP.NET | Web application | GitHub Commit/PR | https://github.com/tmafunisa24-sudo/ITC327W-Project/web | System requires a web interface. | MAFUNISA T
P3-07 | Integration | Shared Process 1 - Web, Supabase and API | GitHub Commit/PR | https://github.com/tmafunisa24-sudo/ITC327W-Project/web | Web interface must connect and communicate with the database. | TAAIBOSCH K
P3-08 | Integration | Shared Process 2 - Mobile, Supabase and API | GitHub Commit/PR | https://github.com/tmafunisa24-sudo/ITC327W-Project/mobile | Mobile interface must connect and communicate with the database. | NDLOVU N
P3-10 | SRS | Project documentation | SRS Section | https://github.com/tmafunisa24-sudo/ITC327W-Project/Technical_Submission_Click_Computer_and_Accessories | SRS is created to review the overall description of the software | WINKEL K, HLALELE D
P3-11 | Microsoft Project | Project schedule, member Resources | Screenshot | https://github.com/tmafunisa24-sudo/ITC327W-Project/project_management/MICROSOFT PROJECT | Microsoft Project is required to outline the tasks and duration of the project. | LJ LESENYEHO
P3-12 | GitHub | Manage github repository | GitHub Commit/PR | https://github.com/tmafunisa24-sudo/ITC327W-Project | Gitub repository is created to manage files of the project. | LESAKO M
P3-13 | Final Demonstration | Finalize research and documentation for presentation. | Screenshot | https://github.com/tmafunisa24-sudo/ITC327W-Project/docs | Findings are used to presenting the work. | TLADI K

## Challenges & Actions
Phase 3 Challenges and Corrective Actions
Date Identified | Development / Integration Challenge | Effect on Progress or Function | Action Taken / Required | Responsible Student | Target Date | Status | Resolved Date | Notes / Known Limitation
2026-10-22 | Integration Challenge: registration credentials - information required to register from the web and mobile application was not stored and connected to the database. | users registering to the system were unable to connect to the database thus hindering them from creating an account. | Too many unnecessary required variables on the database were removed and the link to the database was renamed | LESAKO M | 2026-10-22 | Completed | 2026-11-01
2026-10-18 | Development challenge: ASP.NET - Maintenance records ommitted - Records for repair which are submitted by the client do not appear on the maintenance web page. | Request for customer repairs are stored on the database but do not show on the web page. | Identified the variables at the front-end code references the variables at the back-end. | TLADI K | 2026-10-18 | Completed | 2026-11-01
2026-10-25 | Development challenge: Flutter - Shared layout is not responsive to all mobile devices. | The design layout across all mobile pages do not respond in accordance to the size of the mobile devices. | Ensure all elements and design layout of all mobile pages are responsive to all sizes of all mobile devices. | NOSENGA B | 2026-10-25 | Completed | 2026-11-01
2026-10-22 | Development challenge: ASP.NET - Error on report print-out. | The web application is unable to display the printing configuration/settings before printing the report. | Created an addon on the report page in order to display the printing setting before printing the report. | MAFUNISA T | 2026-10-22 | Completed | 2026-11-01
2026-10-26 | Development challenge: Supabase- Employee enquiries and self-help requests are not clearly specified. | Employee enquiries and self-help desk requests are viewed as similar variables and not catergorized within the database. | Split the variables into two fields within the table to categorize the enquiries and the self-help desk requests. | HLALELE D | 2026-10-26 | Completed | 2026-11-01
2026-10-21 | Development challenge: ASP.NET - Ticket tracking - monitoring the ticket system for each user's request created errors and complications while outputting the time and date of expiry and to which user was it allocated to. | The time and date of the ticket expiry were false and an error message was displayed to which entails an unidentified resource variable. | Used a unique identifier that will allocate the ticket to the rightful user. Creating a countdown system for every ticket issued resolved the issue. | NDLOVU N | 2026-10-21 | Completed | 2026-11-01
2026-10-24 | Development challenge: ASP.NET - Dashboard metrics does not align with the information stored on the database. | Fasle information displayed on both the web and mobile application due to incorrect arthimetical calculation at the back-end code.. | Modified the calculation at the back-end code to display the correct metrics so it corresponds with the information stored on the database. | TAAIBOSCH K | 2026-10-24 | Completed | 2026-11-01
2026-10-20 | Development challenge: Flutter - Notification state remains unchanged. | When a notification was read by a administrator, Its state remains unchanged therefore unread. | When a notification has been read, a command statement from the mobile application must alert the database then the state of notification must be changed from unread to read. | MOLEFE B | 2026-10-20 | Completed | 2026-11-01
2026-10-19 | Development challenge: Flutter - users, admin and technician roles were not properly assigned thus creating wrong executions for different roles. | Users will execute confidential information assigned only for the administrator and technicians will not gain access to maintenance. | Appropriate tasks and executions were displayed depending on the role given for each accounts. | LJ LESENYEHO | 2026-10-19 | Completed | 2026-11-01
2026-10-22 | Development challenge: Github - Documents not properly organized | The asset management codes within the Github repository were misplaced in the wrong directory. | Remove the previous codes from the asset management and push/upload the revelant codes within the correct directory. | WINKEL K | 2026-10-22 | Completed | 2026-11-01
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started

## Phase Summary
Phase 3 Progress Summary
Reporting Period | 18 days |  | Phase 3 Completion Checklist | Complete?
Overall Phase Status | Completed |  | Shared Supabase backend implemented | Yes
What was completed during Phase 3? | Activity 3.1 - Supabase - Required tables, fields, keys and relationships implemented; Activity 3.2 - Supabase - Authentication and access configured where required; Activity 3.3 - Flutter - Approved mobile screens and navigation implemented; Activity 3.4 - Flutter - Main mobile functions connected to Supabase; Activity 3.5 - ASP.NET - Approved web pages and navigation implemented; Activity 3.6 - ASP.NET - Main web functions connected to Supabase; Activity 3.7 - Integration - Shared Process 1 working across the integrated system; Activity 3.8 - Integration - Shared Process 2 working across the integrated system; Activity 3.9 - Integration - Data fields and status values consistent across applications; Activity 3.10 - SRS - Implementation status, approved changes and known limitations updated; Activity 3.11 - Microsoft Project - Schedule updated to reflect actual development progress; Activity 3.12 - Github - Current source code, README and relevant documentation organised; Activity 3.13 - Final demonstration; |  | Main Flutter functions working | Yes
Which functions or processes remain incomplete? | none. |  | Main ASP.NET functions working | Yes
What known limitations remain? | N/A |  | At least two shared processes working | Yes
Which contributions were particularly important? | 1. Flutter Development: This area of development constitues the design and implementation of the mobile application to which is required for phase 3; 2. ASP.NET Development: This area of development constitiues the design and implementation of the web application to which is required for phase 3; 3. Supabase development: This area of development constitues the structure and design of the database to which is required for phase 3; 4. Integration This area of development constitues the shared process of connecting the web and mobile application along with the database into communicating as one systematic entity; 5. Gitub: This area of development manages all project designs, evidence, applications and members' participation within the group. | The project manager's contribution was to ensure all members were available for crucial and urgent meetings when deemed necessary. When members lacked participation or remained absent, it is the project manager's reponsibility to contact, follow-up and enquire an update on each and every members' work; The responsibility of a Github manager contributed by ensuring all files uploaded onto the Github repository were managed, accurate and up-to-date. Members were assisted and informed to upload and identify thier own work onto the repository due to system monitorization; The system design and the prototype was most crucial as it required the collaboration of three members: The database and supbase design analyst, the technical analyst and intergration designer and the UML and process analyst to design, create and integrate the database system and mobile and web applications; Lastly, the responsibility of a stakeholder analyst is one of the most vital contribution to pahse 2. Gathering stakeholder feedback and re-evaluation could shift the entire prespective of the system design. | Integration progress recorded | Yes
Were there participation concerns? | Conflicts emerged amongst members due to work delay and lagging of time; participation amongst the group was a minor issue as few do not assist in contributing. | Conflicts emerged amongst members due to work delay and lagging of time; A member was absent for two consecutive meetings to which raised concerns within the group; Finally, participation amongst the group was a minor issue as few do not assist in contributing. | Implementation evidence recorded | Yes
Is the prototype ready for the final demonstration? | Yes. |  | SRS updated | Yes
Main priority before final presentation | Make sure everyone is assigned for their role when presenting; Understand how the prototypes function (both ASP.NET and Flutter) |  | Microsoft Project updated | Yes
|  |  | GitHub current | Yes
|  |  | Individual contributions recorded | Yes
|  |  | Challenges/actions updated | Yes
|  |  | Known limitations recorded | Yes
|  |  | Group reflection completed | Yes
|  |  | Final demonstration prepared | Yes

## Group Reflection
Phase 3 Group Reflection
1. What did the group complete successfully during development and implementation?
1. Authentication and access control; 2. Tickets - web and API; 3. Tickets - mobile & API; 4. Assets; 5. Maintainance; 6. Departments, users & admin; 7. Notifications, technicians & service catalog; 8. Dashboards & reports; 9. Supabase backend & DevOps; 10. UI shell, documentations & project records.
2. Which development or integration challenges were the most difficult, and how were they addressed?
1. Integration Challenge: registration credentials - information required to register from the web and mobile application was not stored and connected to the database. The issue was resolved - too many unnecessary required variables on the database were removed and the link to the database was renamed; 2. Development challenge: Flutter - users, admin and technician roles were not properly assigned thus creating wrong executions from different roles. The issue was resolved - appropriate tasks and executions were displayed depending on the role given for each accounts.
3. How did the group ensure that Flutter and ASP.NET worked with the same Supabase backend?
The supabase creates a back end table/storage file for both flutter (using the dart file extension) and ASP.NET (using the cs file extension) to connect and link to the external Supabase database. Configuring the app settings and adding relevant addons for API to both applications ensures communication between the backend Supabase tables and the flutter and ASP.Net applications.
4. How was development work divided among group members, and was participation balanced?
Development work was divided according to group member roles. Despite consistent absenteesim and delayed meeting arrival, participation was evenly contributed. Group members reedem by informing the their current work to the project manager.
5. Which parts of the prototype are strongest, and which limitations remain?
Strongest part of the prototype: 1. Dashboard & reports; 2. Maintenance; 3. Notifications. Limitations: None.
6. What did the group learn from developing and integrating the prototype?
1. Both the mobile and web application require an API to communicate with the database; 2. Different applications require different functionalities as they operate with different programming languages; 3. designing and implementing an application rarely correlates with one another due to trials, errors and bugs changing the framework and structure of the initial design.
7. What would the group improve if the project continued beyond the final assessment?
1. Improve on the security control and access against unauthorized access using the 2 factor verification.